## CBA
|  | Year 1 ($) | Year 2 ($) | Year 3 ($) | Year 4 ($) | Year 5 ($) | Total
Benefits
110 | Increased Revenues | 0 | 56000 | 78400 | 109760 | 153664 | 397824
111 | Increased Sales | 0
114 | Decreased Administrative Costs | 0 | 42000 | 43260 | 44557.8 | 45894.534 | 175712.334
115 | Customer Retention | 0
| Total Benefits | 0 | 98000 | 121660 | 154317.8 | 199558.534 | 573536.334
Development costs
211 | Labor: Project Manager | 10200 | - | - | - | - | 10200
212 | Labor: Business Analyst | 14400 | - | - | - | - | 14400
213 | Labor: Senior Developer 1 | 19200 | - | - | - | - | 19200
214 | Labor: Web Designer/Content Manager | 4800 | - | - | - | - | 4800
214 | Labor: Application Developer | 8320 | - | - | - | - | 8320
214 | Labor: Quality Control | 3200 | - | - | - | - | 3200
| Total development costs | 60120 | - | - | - | - | 60120
Operational costs
311 | Software license and renewal | - | 3400 | 3072 | 3072 | 3072 | 12616
312 | Hosting and Infrastructure | - | 12000 | 12000 | 12000 | 12000 | 48000
313 | Database Adminstrator |  | 3006 | 3006 | 3006 | 3006 | 12024
314 | Backup & Disaster Recovery |  | 2200 | 2200 | 2200 | 2200 | 8800
315 | Training & Documentations | - | 3500 | 3500 | 3500 | 3500 | 14000
316 | Security Measures | - | 3400 | 3400 | 3400 | 3400 | 13600
317 | Regulatory Compliance |  | 3200 | 3200 | 3200 | 3200 | 12800
| Total operational costs | 0 | 30706 | 27178 | 27178 | 27178 | 121840
401 | Total costs | 60120 | 30706 | 27178 | 27178 | 27178 | 181960
402 | Net benefits | -60120 | 67294 | 94482 | 127139.8 | 172380.534 | 391576.334
403 | Cumulative Net Cash Flow | -60120 | 7174 | 101656 | 228795.8 | 401176.334
ROI = 391,576/181,960 ​ ×100 ROI=215.04%
Payback Period = YEAR 2

## DETAILS
|  | LY Revenue | Increase % | Total Increase Year 2 | Year 3 | Year 4 | Year 5
110 | Increased Revenues | 40000 | 0.4 | 56000 | 78400 | 109760 | 153664
111 | Increased Sales | 50000 | 0.5 | 75000
**Incremental increase in revenue per year, starting with Year 2 (40% increase over LY), then (40% increase YoY)
|  | Rate | Total # of Hours | Total Amount | Description | Source
211 | Labor: Project Manager | 100 | 102 | 10200 | 512*0.2 | https://www.coursera.org/articles/project-manager-salary
212 | Labor: Business Analyst | 90 | 160 | 14400 | 2hrs/day/4months | https://www.glassdoor.co.in/Salaries/united-states-business-analyst-salary-SRCH_IL.0,13_IN1_KO14,30.htm#:~:text=The%20average%20additional%20cash%20compensation%20for%20a%20Business,Glassdoor%20by%20Business%20Analyst%20employees%20in%20United%20States.
213 | Labor: Senior Developer 1 | 150 | 128 | 19200 | 8hr/week/4months | Compensation Management Solution - CompAnalyst ¦ Salary.com
214 | Labor: Web Designer/Content Manager | 75 | 64 | 4800 | 4hr/week/4months | https://www.coursera.org/articles/project-manager-salary
215 | Labor: Application Developer | 65 | 128 | 8320 | 8hrs/week/4month | https://www.ziprecruiter.com/Salaries/Software-Applications-Developer-Salary-in-Washington,DC
215 | Labor: Quality Control | 100 | 32 | 3200 | 8hrs/month/4month | Salary: Quality Assurance Manager in United States 2024 ¦ Glassdoor
304 | DBA | 160 | 80 | 12800 | 5hr/week/4months
|  | No of Items | Rate | Total Sum |  | Source
216 | Ipads | 3 | 429 | 1287 |  | https://www.amazon.com/dp/B0BJLXMVMV?tag=track-ect-bing-usa-187242-20&linkCode=osi&th=1&psc=1
217 | Monthly Subcriptions | 200 | 4months | 800 |  | https://www.hostgator.com/promo/top10best?clickid=3CvXjzSBzxyNTz%3ARtMS-yR5NUkH1ejwmIzLezo0&irgwc=1&affpat=1&mpid=34020&utm_source=IR&utm_medium=affiliate&utm_campaign=Natural%20Intelligence%20LTD%2C&channelid=P61C46098237S645N0B2A20D0E0000V100&siteID=46098437&irpid=34020
218 | Desktops | 6 | 1000 | 6000 |  | Amazon.com: LG Gram 17" WQXGA Intel Evo Platform Laptop, 13th Gen Intel i7-1360P Processor, 16GB RAM, 2TB SSD, Webcam, Bluetooth, USB-C, Backlit Keyboard, Windows 11, School and Business Ready, LIONEYE Bundle : Electronics
220 | SQL Server License | n/a | n/a | 2000 |  | Microsoft SQL Server 2019 Standard + 10 CALs (trustedtechteam.com)
|  | Year 2 | Year 3 | Year 3 | Year 4
311 | Software license and renewal | 3400 | 3072 | 3072 | 3072 | 2 Operating system/$200/server, Database software $2000, & Development tools framework1000
312 | Hosting and Infrastructure | 12000 | 12000 | 12000 | 12000 | Cloud hosting services (Google Cloud): $500/month/Dedicated server 500/month
313 | Database development and Maintenance | 3006 | 3006 | 3006 | 3006 | 5% of development cost annually 0.05*60120
314 | Backup & Disaster Recovery | 2200 | 2200 | 2200 | 2200 | Backup solutions $100/month/12 ,Recovery planning and periodic testing 1000/yr
315 | Training & Documentations | 3500 | 3500 | 3500 | 3500 | Document creation and meaintenance $1500/qtr, training cost/ qtr $2000
316 | System Security Subscription | 3400 | 3400 | 3400 | 3400 | Security Software and tools $200/month , Regular security Audit $1000/audit/yr
317 | Regulatory Compliance | 3200 | 3200 | 3200 | 3200 | Legal consultations 8hrs/qtr @ $100/hr

## Risk Analysis
Questions | Answer | Rating
How long will it take to implement the proposed project | 1 to 6 months | 1
What are the estimated project costs | $25,000 to $75,000 | 1
Degree of anticipated change to existing business processes: | High | 100
Number of employees impacted by the system | 1 to 20 | 1
Number of agencies impacted by the system | four to Eight | 100
Anticipated user attitude to the new process/system: | Neutral | 100
Number of existing applications that must feed or receive data from the new system | 0 | 1
Volume of required data to be converted from existing system to new system: | None | 1
Complexity of the required conversion | No Conversion Required | 1
Will the system be implemented with an off-the-shelf system | No | 500
Has the Titans Food developed/implemented system similar in size and complexity in the past | No | 500
Project teams level of experience with the business process being impacted | Medium | 100
Titans Food staffs experience with implementing systems with similar technologies | Low | 250
Support of Department Head (s) and Senior Managers in the impacted agencies | High | 1
Other external entity, such as the State, is involved in the project | External Entity is Playing a Minnor Roles | 250
Project Score : 1803
Risk Assessment based on Project Score range from 1,001 to 2,500 (Low Risk)